# CSCI 427 Capstone II

# Spring 2020

# Phased Implementation Plan

# The Skyentists

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Requirement reference code or number | Description | Person(s) responsible | Estimated  hours | Notes |
| **Phase 1 (due 1/31/20)** | **Yellow Highlight** |  |  |  |
| *FR-HP02* | *Create a Test Config File (using data provided by client)* | *Mark* | *15* |  |
| *FR-HP03* | *Create Config File Parser* | *Jake* | *10* |  |
| *FR-HP10* | *Create Config File Generator* | *Jake* | *10* |  |
|  | *Make Class Skeletons for GPP and RECO* | *Lucas* | *14* | *Not in Requirements Doc* |
| *FR-HP01* | *Calculate dominant PFT for each tower site* | *Max* | *7* |  |
| *FR-HP04* | *Functionality to choose 1 PFT at a time* | *Max* | *3* |  |
| *FR-HP06* | *User chooses which outliers to optimizing GPP and RECO* | *Lucas* | *6* |  |
| *FR-HP11* | *Calculate flux tower weights (some towers in same 9km)* | *Mark* | *5* | *Work with Max* |
| *FR-MP01/*  *FR-MP05* | *Calculate area percentage for each PFT for each site and compile ancillary info* | *Jake* | *5* |  |
| *FR-MP03* | *Subset time series variable to user configurable period* | *Lucas* | *5* |  |
| *FR-MP02/*  *FR-MP07* | *Compile historical data for each PFT (table) and report average data for PFT each day of year* | *Max* | *3* |  |
| *FR-MP04* | *Subset meterological and reference input to dominant PFT* | *Max* | *2* |  |
| *FR-MP06* | *Compile all data for updated BPLUT* | *Mark* | *3* |  |
|  |  |  |  |  |
| **Phase 2 (due 2/21/20)** | **Green Highlight** |  |  |  |
| *FR-HP05* | *Guide user through removing outliers in referenced GPP and RECO* | *TBD* | *TBD* |  |
| *FR-HP08* | *Specify numerical spin-up iterations* | *TBD* | *TBD* |  |
| *FR-MP15* | *Run analytical and numerical model spin-ups* | *TBD* | *TBD* |  |
| *FR-MP18* | *Prepare vectors of initial optimized params to iteratively change* | *TBD* | *TBD* |  |
| *FR-HP07* | *Calculate GPP and RECO linear ramp functions* | *TBD* | *TBD* |  |
| *FR-MP12/*  *FR-MP13* | *Calculate Cbar after optimization and plot Rh/Cbar vs TSOIL and SMSF* | *TBD* | *TBD* |  |
| *FR-MP08* | *Display ramp functions and give option to save plots as file* | *TBD* | *TBD* |  |
| *FR-MP11* | *User edits Pk and Prh for RECO* | *TBD* | *TBD* |  |
| *FR-LP01* | *Remove negative values in annual GPP/RECO for each tower site* | *TBD* | *TBD* |  |
|  |  |  |  |  |
| **Phase 3 (due 3/13/20)** | **Blue Highlight** |  |  |  |
| *FR-HP09* | *Compute comprehensive validation and fit statistics* | *TBD* | *TBD* |  |
| *FR-MP10* | *Report differences between new and old parameters after optimization* | *TBD* | *TBD* |  |
| *FR-MP16* | *Run spin-up from 2000-2019* | *TBD* | *TBD* |  |
| *FR-MP09* | *Allow plot of GPP against Emult* | *TBD* | *TBD* |  |
| *FR-MP14* | *Calculate σ and Bsoc for each tower site to plot σ \* Bsoc against ground truth SOC sizes* | *TBD* | *TBD* |  |
| *FR-MP19* | *Calculate GPP\*, Kmult\*, NPP\* based off calculations* | *TBD* | *TBD* |  |
| *FR-MP17* | *Run L4C soil model forward runs* | *TBD* | *TBD* |  |
| *FR-LP02* | *Calculate lower and upper limits for APAR* | *TBD* | *TBD* |  |
|  |  |  |  |  |
| **Phase 4 (due 4/17/20)** | **Pink Highlight** |  |  |  |
| *FR-MP20* | *Calculate RMSE for each subset of towers* | *TBD* | *TBD* |  |
| *FR-MP21* | *Calculate NEE and reports stats* | *TBD* | *TBD* |  |
| *FR-LP03* | *Plot GPP against Emult and Rh/Cbar against Kmult* | *TBD* | *TBD* |  |
|  |  |  |  |  |
|  |  |  |  |  |